## Sheet2
Physical progress of works under different Scheme/Programmes/Projects across department of current years, Annexure C
Sl No | Admin Department | Name of scheme | Nos of works senction in current years | Progress of current years works/ services- categories nos of works base on stage of physical progress | [5 empty] | Remarks
|  |  |  | 100% | 75-99% | 50-74% | 25-49% | 1-25% | Not Started
1 | SSA | Additional Classroom | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 3rd installment yet to receive
2 | SSA | Boys Toilet | 30 | 0 | 0 | 0 | 29 | 0 | 0
3 | SSA | Girls Toilet | 19 | 0 | 0 | 0 | 12 | 0 | 0
4 | SSA | Ramp | 15 | 15 | 9 | 0 | 0 | 0 | 0
5 | SSA | Repair of Girls Toilet | 12 | 12 | 0 | 0 | 0 | 0 | 0
6 | SSA | Repair of Boys Toilet | 14 | 14 | 8 | 0 | 0 | 0 | 0
7 | SSA | Boundary wall | 10 | 0 | 0 | 0 | 10 | 0 | 0
I/S Cum DMC SSA,Baksa

## Sheet3
Physical progress of works under different Scheme/Programmes/Projects across department - of Previous year Annexure -D
Sl No | Admin Department | Name of scheme | Total number of works pending as on last date of previous financial year | Number of years delayed for completion -as on last date of last financial year- categories works base on the delay of completion |  |  |  |  | Progress of previous years pending as on the last date of last financial/ categories wise works based on the stage of physical progress | [5 empty] | Remarks
|  |  |  | less than 1 year | >=1 to <3 yrs | >=3 to<5yrs | >=5yrs | Total | 100% | 75-99% | 50-74% | 25-49% | 1-25% | Not Started
1 | SSA | Major Repair | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3rd installment yet to receive
I/S Cum DMC SSA,Baksa

## Sheet1
Annexure-A
Monthly status of Fund receipt and utilisation for the Month of June /2023
A. For Schemes: Fund received
SI. No. | Admin. Dept. | Name of Scheme (+Inplementation Agency) | PFMS Code & SLS Code | Category CS/CSS/State/EAP etc. | Opening Balance with CAN/SNA/Others-as applicable. |  | Opening Balance with the District/Council/Others as applicable |  | Current Year Allocation to District* |  | Fund received in the current Year |  | Total funds available for Scheme | Funds Utilised till now Amount & (%in bracket) |  | Amount for which Ucs are pending at the end of previous year | Utilisation Certificate submitted against total available funds for the current year | Amount for which Ucs are pending as on date. |  | Remarks
[5 empty] | Central Share | State Share | Central Share | State Share | Central Share | State Share | Central Share | State Share |  | Central Share | State Share |  |  | Of Previous Year | Of Current Year
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Edu | SSA | ASLA00000004 | CSS | 0 | 0 |  |  | 69.1895 | 0 | 34.3 | 0 | 34.2995 | 34.2995 | 0 | no | yes | no | no
*= will be provided by the HOD/Concerned Agency. PFMS: Public Finance Management System, SLS:State Linked Scheme-State Code.
Annexure-B
B. Schemes for which no funds are received by the District/Council: For (Please visit httpps//indiabudget.gov.in/index.php and concerned Ministry/Department website to know the list of Central schemes of current and previous years)
SI. No. |  | Administrative Department | [5 empty] | Scheme Name | [5 empty] | Reasons |  |  |  | Remarks if any
1
2
I/S Cum DMC SSA, Baksa